## Spend Profile
Description | Automatic Spend Profile Desc. | Cost | Payment Schedule 1 (Date) | Payment Schedule 1 (%) | Payment Schedule 2 (Date) | Payment Schedule 2 (%) | Payment Schedule 3 (Date) | Payment Schedule 3 (%) | % Check
Choke | Choke | 50000 | 60 | 100% | 0 | 0% | 0 | 0% | 100%
Meter | Meter | 450000 | 90 | 100% | 0 | 0% | 0 | 0% | 100%
Pipe | Pipe | 25000 | 30 | 100% | 0 | 0% | 0 | 0% | 100%
Labour - Mech | Compressor | 150000 | 360 | 50% | 180 | 30% | 30 | 20% | 100%
Labour - Elec | Labour - Elec | 150000 | 0 | 100% | 0 | 0% | 0 | 0% | 100%
Test | Default/Other | 200000 | 0 | 100% | 0 | 0% | 0 | 0% | 100%
Test 2 | Default/Other | 500000 | 0 | 100% | 0 | 0% | 0 | 0% | 100%
Group Sep | Group Sep | 500001 | 180 | 50% | 90 | 30% | 0 | 20% | 100%
Compressor | Compressor | 500000 | 360 | 50% | 180 | 30% | 30 | 20% | 100%
Meter (Special) | Default/Other | 55000 | 245 | 70% | 93 | 30% | 0 | 0% | 100%

## Conditions
Condition | Variable
Onstream Date | 10/01/2026
Construction Days | 30
Project Window | 375

## Cost Estimate Templated
Description | Payment Schedule 1 (Date) | Payment Schedule 1 (%) | Payment Schedule 2 (Date) | Payment Schedule 2 (%) | Payment Schedule 3 (Date) | Payment Schedule 3 (%) | % Check
Default/Other | 0 | 100% |  |  |  |  | 100%
Choke | 60 | 100% |  |  |  |  | 100%
Compressor | 360 | 50% | 180 | 30% | 30 | 20% | 100%
Group Sep | 180 | 50% | 90 | 30% | 0 | 20% | 100%
Labour - Elec | 0 | 100% |  |  |  |  | 100%
Labour - Mech | 0 | 100% |  |  |  |  | 100%
Meter | 90 | 100% |  |  |  |  | 100%
Pipe | 30 | 100% |  |  |  |  | 100%